## Sheet1
Cost Estimate
Project Name: Hunt Game App Development (HGAD) | Date: 08/24/2020
WBS Categories | Total Team Cost | Number of hours per week | Total cost per week | Total cost for three sprints | Designation | $/hour
1. Initiating | 390 | 12 | 4680 | 28080 | Team Leader and Full Stack Developer | 70
2. Planning | 390 | 12 | 4680 | 28080 | Project Manager | 70
3. Designing | 390 | 48 | 18720 | 112320 | Full stack Developer | 65
3.1 UI Design |  | 12 | 0 | 0 | UI Developer | 65
3.2 Synthesis of Design |  | 12 | 0 | 0 | Database Engineer | 60
3.3 Implementation Iteration |  | 12 | 0 | 0 | Front end Developer and Testing | 60
3.4 Early release and Contract finalization |  | 12 | 0 | 0 |  | 390
4. Implementation | 390 | 48 | 18720 | 112320
4.1 Application Developer |  | 24 | 0 | 0
4.2 PWA Implementation |  | 24 | 0 | 0
5. Monitoring and Controlling | 390 | 12 | 4680 | 28080
6. Closing | 390 | 12 | 4680 | 28080
Total |  |  | 56160 | 336960